## Development
No. | Module | Feature | Description | Priority | Status | Remarks
1 | Platform | Cloud-based LMS |  |  | Done | Env-driven config throughout (backend/src/app.js uses process.env.CLIENT_URL, backend/server.js uses process.env.PORT, backend/src/config/db.js connects via process.env.MONGO_URI to Atlas), /health liveness endpoint, Cloudinary + Stripe cloud services wired in. No Dockerfile/render.yaml in repo, but no hardcoded localhost-only assumptions in server code.
2 | Platform | Progressive Web App (PWA) |  |  | Done | frontend/public/manifest.webmanifest, frontend/public/sw.js registered in frontend/src/main.jsx, frontend/public/offline.html present. Hand-written service worker is a network passthrough (no offline content caching), not a vite-plugin-pwa build.
3 | Platform | Cross-platform Access |  |  | Done | Responsive Tailwind breakpoints (sm:/md:/lg:) used throughout Mwasalat pages; PWA install prompt (MwasalatInstallPrompt.jsx) covers cross-device access. No native mobile app.
4 | Platform | Arabic & English |  |  | Done | Real i18next setup (frontend/src/lib/mwasalatI18n.js) loading separate en.json/ar.json bundles per section from frontend/src/locales/mwasalat/; MwasalatLanguageToggle.jsx switches language live.
5 | Platform | RTL Support |  |  | Done | MwasalatLanguageToggle.jsx sets document.documentElement.dir = 'rtl'/'ltr' and syncs lang attribute — genuine RTL layout switching, not a stray CSS class.
6 | Platform | Multi-tenancy |  |  | Partial | No true multi-tenant/multi-organization model — single Mwasalat instance with department-level data scoping only (mwasalatDepartmentScope.js: only department_admin role is query-filtered by department). No per-tenant isolation or org switching.
7 | Platform | Self-registration |  |  | Done | POST /mwasalat-auth/register (mwasalatAuth.routes.js) hardcodes role to LEARNER/EXTERNAL_LEARNER, no admin involvement required — matches PRD's students-only self-registration rule.
8 | Platform | Course Catalog Search |  |  | Done | MwasalatCoursesCatalogPage.jsx has real client-side search/filter by title/category (incl. Arabic fields) plus category/sub-category drill-down.
9 | Platform | Long-term Maintainability |  |  | Not Started | Process commitment (long-term maintainability posture, not a discrete code feature) — N/A for repo audit.
10 | System | Scalable Architecture |  |  | Done | Layered routes→controller→service→model architecture per module, 34 Mongoose .index() calls across models, express-rate-limit at app and auth level, Atlas-managed connection pooling.
11 | System | Role-based Access |  |  | Done | mwasalatAuthMiddleware.authenticate / authorize(...roles) (mwasalatAuth.middleware.js), role constants in mwasalatUser.constants.js, applied across all route files.
12 | System | Course Management |  |  | Done | Full course CRUD in mwasalatProgram module — model supports pdf/recording/live/ILT content types with create/update/delete routes and service logic. Course creation now also captures internal-vs-external audience targeting (department list and/or ad-hoc MwasalatGroup cohorts) and an isMandatory flag; marking a course mandatory auto-enrolls every matching internal learner immediately (mwasalatProgram.service.js syncMandatoryEnrollmentsForProgram/syncMandatoryEnrollmentsForLearners), including learners who join a matching department/cohort afterward (hooked from mwasalatUser bulkImport/assignDepartment and mwasalatGroup create/update).
13 | Course Management | Curriculum Grouping |  |  | Partial | Only category/subCategory string fields plus a single prerequisiteProgram chain (mwasalatProgram.model.js) — no dedicated curriculum/learning-path entity grouping multiple courses.
14 | Course Management | H5P Interactive Content |  |  | Not Started | No H5P reference anywhere in backend or frontend. Content types are limited to PDF, recording, live, ILT (CONTENT_TYPES in mwasalatProgram.constants.js) — no interactive-content embed mechanism.
15 | Course Management | SCORM Support |  |  | Not Started | No SCORM reference in the codebase — no package upload/extraction/runtime player; course content is PDFs, recordings, or live/ILT sessions only.
16 | Course Management | xAPI Support |  |  | Not Started | No xAPI/Tin Can reference anywhere — no statement-store client, no LRS integration.
17 | Course Management | Course Expiry |  |  | Done | MwasalatProgram.expiryDate enforced by hourly cron archiveExpiredMwasalatPrograms (scheduler.js) auto-archiving past-expiry programs; separate certificateValidityMonths field with its own auto-renew/reminder crons.
18 | Course Management | Course Prerequisites |  |  | Done | prerequisiteProgram ref field on the program model, enforced server-side in enroll() (blocks with 409 until prior course is completed), with a prerequisite dropdown in MwasalatAddCoursePage.jsx.
19 | Course Management | Content Retirement |  |  | Done | PROGRAM_STATUS.ARCHIVED soft-retires courses (remove() sets status, not hard delete), notifies enrolled learners, excluded from catalog queries; admin UI has an archived status filter (MwasalatAdminProgramsPage.jsx).
20 | User Management | CSV User Import |  |  | Done | bulkImport() in mwasalatUser.service.js is Department Admin-only (POST /bulk-import requires department_admin; platform_admin no longer has access) and auto-assigns each imported row to the actor's own department, so imports are immediately visible in that department's roster; still learner-only (instructors use invite flow per project convention).
21 | User Management | Supervisor Assignment |  |  | Done | supervisor ref field on MwasalatUser, assignSupervisor() route (platform-admin only), dedicated SUPERVISOR role, and a 'My Team' roster dashboard (MwasalatSupervisorDashboard.jsx).
22 | User Management | Cohort Management |  |  | Done | Dedicated MwasalatGroup model/module (cohort with member list) with admin UI at MwasalatAdminCohortsPage.jsx. Now actually wired into mandatory-training targeting as described: a course's targetGroups field (mwasalatProgram.model.js) can target one or more cohorts independently of department, and adding a member to a targeted cohort auto-enrolls them into that course's mandatory training (mwasalatGroup.service.js create/update).
23 | User Management | Dormant User Management |  |  | Partial | Dormant detection exists only client-side (isDormant() 30-day rule in MwasalatLearnersPage.jsx with a 'Dormant' filter) — no backend scheduled sweep, no automatic deactivation, no dormant-specific bulk action.
24 | Learning Delivery | Instructor-Led Training (ILT) |  |  | Done | iltVenue/iltScheduledAt/capacity fields on the program model; enrollment consumes seats, waitlisting/promotion applies, attendance tracked via MwasalatAttendance model. Instructor now has a "Mark Class Completed" action (MwasalatProgramDetailPage.jsx check-in card -> POST /:id/complete-class -> iltClassCompletedAt) separate from attendance, which gates the course quiz (mwasalatQuiz.service.js submitAttempt via isClassSessionCompleted). Once iltScheduledAt has passed, the course is also hidden from the public browse catalog (mwasalatProgram.service.js listPublic) while existing enrollees keep full access via getById/My Courses.
25 | Learning Delivery | Virtual Instructor-Led Training (VILT) |  |  | Done | Real Zoom Server-to-Server OAuth integration (backend/src/integrations/zoom.js) creates live meetings via the Zoom API; wired into program service with host-only start-URL handling. Same "Mark Class Completed" action applies to live classes (liveClassCompletedAt), gating the course quiz until the instructor confirms the session ran — previously the quiz unlocked the moment a learner clicked Join. Courses past their liveScheduledAt are hidden from the public browse catalog but remain accessible to already-enrolled learners.
26 | Learning Delivery | Waitlist Management |  |  | Done | ENROLLMENT_STATUS.WAITLISTED fully implemented — auto-waitlist when capacity full, promoteFromWaitlist() fills freed seats oldest-first with notification, learner sees waitlistPosition.
27 | Learning Delivery | QR Code Attendance |  |  | Done | QR check-in: instructor course page renders a QR code encoding a /learner/check-in/:id URL; scanning hits checkIn()/recordAttendance() creating an MwasalatAttendance record. Manual 'mark present' fallback also available.
28 | Learning Delivery | Approval Workflows |  |  | Done | program.requiresApproval gates new enrollments into PENDING_APPROVAL; approveEnrollment()/rejectEnrollment() handle instructor/admin approval with learner notification.
29 | Learning Delivery | Competency Framework |  |  | Not Started | No 'competency' or skills-framework terminology/model anywhere — no skill tagging on programs, no competency-to-course mapping, no gap-analysis reporting.
30 | Learning Delivery | Learning Plans |  |  | Not Started | No learning-plan/learning-path construct — discovery is catalog-browse plus AI keyword-based suggestions only, no assignable individual learning-path entity.
31 | AI | AI Recommendations |  |  | Partial | No dedicated recommendation engine — the learner dashboard's 'Recommended' widget is a plain not-enrolled filter, not AI-scored; the AI chat's browseAvailablePrograms tool offers conversational discovery only, not personalized scoring.
32 | AI | AI Quiz Generation |  |  | Done | mwasalatAi.service.js generateQuizQuestions() calls Gemini with a structured JSON schema to draft MCQ questions from course title/description; wired via mwasalatQuiz.service.js aiGenerateQuestions() and a 'Generate with AI' button in MwasalatQuizBuilder.jsx. Instructor reviews/edits before saving.
33 | AI | Learning Analytics |  |  | Done | mwasalatAi.tools.js/instructorTools.js expose real AI-chat analytics (revenue trends, enrollment risk, quiz pass rates, attendance, certificate expiry) with chart/table rendering; complemented by role dashboards (instructor/admin/supervisor) computing completion rate, at-risk counts, and ratings outside the AI chat.
34 | Learning | Gamification |  |  | Partial | Points (POINTS_PER_PASS), engagement streaks with 7/30/100-day milestone notifications, and an Achievements page exist — but no badge catalog and no leaderboard/peer-ranking feature.
35 | Communication | Email Notifications |  |  | Done | Real SMTP email via backend/src/utils/mailer.js (nodemailer), used for verification/reset, certificate/reminder emails, etc. Falls back to dev-log-only when SMTP env vars are unset.
36 | Communication | SMS Notifications |  |  | Not Started | No SMS gateway code anywhere in backend/src (no Twilio/SMS provider integration found).
37 | Communication | WhatsApp Notifications |  |  | Not Started | No WhatsApp Business API / Twilio WhatsApp integration found anywhere in the repo.
38 | Communication | Automated Reminders |  |  | Done | backend/src/services/scheduler.js runs node-cron jobs: hourly program-expiry archive, daily engagement/inactivity nudges, weekly instructor digest, daily certificate-expiry reminders and auto-renewal.
39 | Communication | Course Forums |  |  | Done | Full mwasalatDiscussion module — per-course threaded forum (create/reply/pin/resolve/moderate/delete) with live Socket.io updates; frontend pages for learner and instructor.
40 | Communication | Global Announcements |  |  | Done | mwasalatNotification.service.js create() lets admins broadcast a title/message to all users or by role, delivered via Socket.io + persisted with read/unread tracking (MwasalatAdminAnnouncementsPage.jsx).
41 | Assessment & Certification | Quiz Engine |  |  | Done | mwasalatQuiz.service.js submitAttempt() validates answers, grades MCQ, computes score/pass, records attempts, awards points once, and triggers certificate issuance — a complete engine, not a stub. For live/ILT courses, submitAttempt() now also requires the instructor to have marked the session complete (isClassSessionCompleted in mwasalatProgram.service.js) before an attempt is accepted, not just that the learner opened/checked into the content.
42 | Assessment & Certification | Adaptive Assessments |  |  | Not Started | mwasalatQuiz.model.js has a flat fixed question array with one passPercentage — no difficulty field, branching, or adaptive selection logic anywhere in the quiz/attempt code.
43 | Assessment & Certification | Certificate Generation |  |  | Done | MwasalatCertificate model (learner/program/issuedAt/expiresAt), formatCertificateNumber(), learner-facing print-to-PDF certificate page, and a public verify-certificate page.
44 | Assessment & Certification | Auto-renewing Certifications |  |  | Done | Per-program autoRenewCertificate + certificateValidityMonths flags; autoRenewExpiringCertificates() runs daily via scheduler extending expiry before lapse; non-auto-renew courses get expiry reminders and retest-based reissue.
45 | Assessment & Certification | Survey Management |  |  | Not Started | MwasalatFeedbackPage.jsx is a fixed 2-star rating (course/instructor) + free-text comment tied 1:1 to a course — not a configurable survey builder; no separate survey model exists.
46 | Reports & Analytics | Standard Reports |  |  | Done | MwasalatAdminSalesReportPage.jsx (revenue/sales stats, trend chart, top programs, Excel export) plus dedicated certificates/quiz-results/activity-log admin report pages.
47 | Reports & Analytics | Custom Reports |  |  | Partial | No dedicated custom-report-builder UI (no column/metric picker or saved custom reports). Closest equivalent: sales-report date-range presets and the AI assistant's ad hoc natural-language querying with chart/table rendering.
48 | Reports & Analytics | CPD Tracking |  |  | Not Started | 'CPD' only appears as a category-name keyword heuristic (mwasalatProgram.suggestions.js) for cosmetic catalog categorization — no CPD credit/hour field, accrual, or tracking logic on any model.
49 | Reports & Analytics | Learner Transcripts |  |  | Done | MwasalatTranscriptPage.jsx — full print/PDF-ready learner transcript covering enrollments, quiz-attempt history, and certificates with numbers/expiry.
50 | Reports & Analytics | Certification Reports |  |  | Done | MwasalatAdminCertificatesPage.jsx lists every issued certificate platform-wide with learner, course, issue date, certificate number, and expiry status — a dedicated certification report distinct from the general sales/quiz reports.
51 | Administration | Web-based Administration |  |  | Done | Full admin page set (MwasalatAdminDashboard.jsx, MwasalatAdminProgramsPage.jsx, MwasalatAdminStaffPage.jsx, etc.) under MwasalatAdminLayout.jsx.
52 | Administration | Configurable File Upload Limits |  |  | Partial | backend/src/middlewares/upload.js defines per-type multer size limits (avatar/PDF/course files/CSV/assignments) but these are hardcoded constants, not exposed as admin-configurable settings.
53 | Administration | User Timezone Support |  |  | Partial | Implemented as a platform-wide timezone setting (not per-user): a 'timezone' field on the MwasalatSettings singleton (backend/src/modules/mwasalatSettings/mwasalatSettings.model.js, default 'Asia/Muscat'), editable via MwasalatAdminSettingsPage.jsx. backend/src/utils/orgTimezone.js computes org-local day/month boundaries from it and is wired into: cron job scheduling (scheduler.js, was hardcoded Asia/Kolkata), the Zoom meeting display zone (zoom.js, was hardcoded UTC), the instructor 'Today's Schedule' widget (mwasalatProgram.service.js getMyTodaySchedule, was the server OS zone), and the Sales Report date-range filter/trend buckets (mwasalatPayment.service.js, was assuming UTC midnight). Remaining gap: no per-user override — all learners/instructors see times in this single org zone, judged sufficient for this single-country (Oman) platform.
54 | System | Background Job Scheduler |  |  | Done | backend/src/services/scheduler.js uses node-cron for 5 scheduled jobs (program-expiry archive, engagement sweep, instructor digest, cert-expiry reminders, cert auto-renewal).
55 | Security | Password Policy |  |  | Done | backend/src/utils/passwordPolicy.js enforces an 8+ char / upper+lower+digit password regex via assertStrongPassword(), applied on register and change-password.
56 | Security | CAPTCHA Protection |  |  | Done | Custom math-based CAPTCHA (backend/src/utils/mwasalatCaptcha.js + frontend MwasalatCaptcha.jsx) verified server-side on register — not a third-party reCAPTCHA, but functions as real bot protection.
57 | Security | Session Timeout |  |  | Done | JWT access token 15m / refresh 7d, plus a real 30-minute idle-activity auto-logout guard (MwasalatIdleLogoutGuard.jsx) tracking mouse/keyboard/touch activity.
58 | Security | Consent Management |  |  | Done | Registration requires a consentAccepted boolean (rejected if false) and persists a consentAcceptedAt timestamp on the user model.
59 | Security | Two-Factor Authentication (TOTP) |  |  | Done | Optional TOTP-based 2FA (RFC 6238, via otplib) users opt into post-login — not required at registration. POST /mwasalat-auth/2fa/setup¦enable¦disable manage it (mwasalatAuth.routes.js, setupTwoFactor/enableTwoFactor/disableTwoFactor in mwasalatAuth.service.js); secret stored AES-256-GCM encrypted (backend/src/utils/encryption.js) with bcrypt-hashed one-time backup codes. When enabled, login returns a challengeToken instead of tokens until POST /mwasalat-auth/2fa/verify confirms a TOTP or backup code (verifyTwoFactorLogin). Frontend: MwasalatTwoFactorSettings.jsx (setup/enable/disable), MwasalatTwoFactorChallenge.jsx (login verification).

## Hosting_DevOps
No. | Module | Feature | Description | Priority | Status | Remarks
1 | Infrastructure | Cloud VPS Deployment |  |  | Not Started | No Dockerfile, docker-compose, PM2 ecosystem file, or render/railway/vercel config found anywhere in the repo.
2 | Platform | Data Sovereignty Ready |  |  | Done | backend/src/config/db.js calls mongoose.connect(process.env.MONGO_URI) — fully env-driven, no hardcoded host/region.
3 | Infrastructure | Redis Caching |  |  | Not Started | No redis/ioredis dependency or usage anywhere; backend/src/sockets/socket.js explicitly notes in-memory/single-process only, no Redis adapter.
4 | Infrastructure | Infrastructure Scalability |  |  | Partial | Stateless JWT auth supports horizontal API scaling, but socket.js tracks online users via in-memory Maps with no Redis/sticky-session adapter — breaks under multi-instance deployment.
5 | Security | SSL / HTTPS |  |  | Partial | helmet() applied (sets HSTS by default) and app.set('trust proxy', 1) confirms TLS termination is expected at a reverse proxy — no explicit HTTP-to-HTTPS redirect middleware in app code.
6 | Security | Data Encryption at Rest |  |  | Done | Passwords hashed with bcrypt (rounds 12); reversible AES-256-GCM field-level encryption for 2FA TOTP secrets (backend/src/utils/encryption.js). DB-at-rest encryption is MongoDB Atlas provider-managed, outside app code.
7 | Infrastructure | Automated Backups |  |  | Not Started | No backup scripts/cron jobs for DB dumps in the repo; MongoDB Atlas backups are provider-managed, outside repo scope.
8 | Infrastructure | System Monitoring |  |  | Done | winston logger writes logs/error.log + logs/combined.log, plus morgan HTTP request logging. No APM/Sentry integration.
9 | Administration | Patch Management |  |  | Done | .github/dependabot.yml runs weekly dependency-update PRs for backend/frontend/github-actions; a dependency-audit workflow runs npm audit on push/PR/weekly schedule.
10 | Security | SSH / Secure Server Access |  |  | Not Started | Infra/hosting-provider responsibility (SSH/server access) — no code surface in this repo.

## Client_Dependencies
No. | Module | Feature | Description | Priority | Status | Remarks
1 | Branding | Custom Branding |  |  | Done | frontend/tailwind.config.js defines mwasalatRed/mwasalatInk brand tokens; logo assets present (mwasalat-logo.png, mwasalat-mark.png).
2 | Security | SAML2 SSO |  |  | Not Started | No SAML reference anywhere in the repo (backend or frontend).
3 | User Management | LDAP / Active Directory Synchronization |  |  | Not Started | No LDAP reference anywhere in the repo.
4 | User Management | Automatic User Provisioning |  |  | Not Started | No SSO/SCIM-based auto-provisioning — users are created via self-registration or manual admin/invite creation only.
5 | Security | OAuth2 Authentication |  |  | Done | mwasalatAuth.service.js imports OAuth2Client from google-auth-library, configured via GOOGLE_CLIENT_ID, for learner Google login.
6 | Integrations | HRMS Integration |  |  | Not Started | No HR system integration found anywhere in the repo.
7 | Integrations | Zoom Integration |  |  | Done | backend/src/integrations/zoom.js implements Server-to-Server OAuth and createZoomMeeting() against the live Zoom API, with graceful fallback to manual meeting links if unconfigured.
8 | Integrations | Microsoft Teams Integration |  |  | Not Started | Only incidental mentions of 'Teams' as a meeting-link option string in instructor-facing text — no real Microsoft Graph/Teams API integration.
9 | Integrations | Payment Gateway Integration |  |  | Done | mwasalatPayment.service.js fully implements Stripe checkout (OMR/baisa conversion) with webhook handling and a transaction model.
10 | Integrations | Google Analytics Integration |  |  | Done | MwasalatAnalytics.jsx loads gtag.js from a configurable GA measurement ID env var and fires SPA page_view events on route change.
11 | Communication | SMTP Configuration |  |  | Done | .env.example defines SMTP_HOST/PORT/USER/PASS/FROM; nodemailer reads these for transport config (backend/src/utils/mailer.js).
12 | Communication | SMS Gateway |  |  | Not Started | No SMS provider (Twilio/MSG91/etc.) integration found anywhere in the repo.
13 | Communication | WhatsApp Business API |  |  | Not Started | No WhatsApp reference found anywhere in the repo.
14 | AI | OpenAI/API Configuration |  |  | Done | mwasalatAi.service.js uses GoogleGenAI (@google/genai) configured via GEMINI_API_KEY/GEMINI_MODEL env vars, with full tool-calling per role.
15 | Mobile | Push Notification Configuration | Browser/PWA push notifications (Web Push via VAPID) so learners and staff get notified of new announcements, grades, and reminders even when the app tab or window is closed. | Medium | Done | Implemented as browser Web Push (not native FCM/APNs — there's no separate native mobile app in this repo): VAPID key pair + web-push in backend/src/integrations/webPush.js, MwasalatPushSubscription model, subscribe/unsubscribe endpoints on mwasalatNotification routes, and push/notificationclick handlers in frontend/public/sw.js. Wired into mwasalatNotificationService.create() (admin broadcasts) and notifyUsers() (all targeted notifications: grades, reminders, approvals, etc.), so every existing notification path now also fires a push. Learners/staff opt in via an 'enable notifications' prompt in MwasalatNotificationBell.

## Support_PostGoLive
No. | Module | Feature | Description | Priority | Status | Remarks
1 | Support | Context-sensitive Help |  |  | Not Started | No dedicated help/tooltip component or help-center page — only incidental native title= attributes on a few icon buttons, not a designed contextual-help system.
2 | Support | Helpdesk Support |  |  | Not Started | Process/service deliverable, not a code feature — out of scope for the repo.
3 | Support | Administrator Training |  |  | Not Started | Process/service deliverable, not a code feature — out of scope for the repo.
4 | Support | Trainer Training |  |  | Not Started | Process/service deliverable, not a code feature — out of scope for the repo.
5 | Support | Learner Orientation |  |  | Not Started | No onboarding tour/walkthrough library or component found in the frontend.
6 | Support | User Documentation |  |  | Not Started | Only a 3-line placeholder README.md at repo root; no /docs folder or in-app user documentation/help pages.
7 | Support | Training Video Library |  |  | Not Started | No video library/tutorial page component found in the frontend.
8 | Support | Service Reporting |  |  | Not Started | Process/service deliverable, not a code feature — out of scope for the repo.