## Development
No. | Module | Feature | Status | Remarks
1 | Platform | Cloud-based LMS | Done
2 | Platform | Progressive Web App (PWA) | Done
3 | Platform | Cross-platform Access | Done
4 | Platform | Arabic & English | Done
5 | Platform | RTL Support | Done
6 | Platform | Multi-tenancy | Partial
7 | Platform | Self-registration | Done
8 | Platform | Course Catalog Search | Done
9 | Platform | Long-term Maintainability | Not Started
10 | System | Scalable Architecture | Done
11 | System | Role-based Access | Done
12 | System | Course Management | Done
13 | Course Management | Curriculum Grouping | Partial
14 | Course Management | H5P Interactive Content | Not Started | Native interactive learning content is supported. H5P package compatibility is not currently included.
15 | Course Management | SCORM Support | Not Started | Native course management is fully supported. Third-party SCORM package import is not currently included.
16 | Course Management | xAPI Support | Not Started | Native learner progress tracking, assessments, and learning analytics are fully supported. xAPI interoperability is not currently included.
17 | Course Management | Course Expiry | Done
18 | Course Management | Course Prerequisites | Done
19 | Course Management | Content Retirement | Done | Deletion is a soft-archive (mwasalatProgram.service.js#remove) — now guarded: blocked outright (409) while any learner has a non-terminal enrollment (pending_approval/waitlisted/enrolled/in_progress/locked), no bypass even for super_admin. New enrollmentClosed toggle (model field + update()/enroll()/listPublic()) lets an instructor stop new sign-ups while existing learners finish. Once no active enrollments remain, delete schedules a 5-day grace-period archive (deletionScheduledAt field, auto-closes enrollment, notifies learners with the date, cancellable via POST /:id/cancel-deletion) instead of archiving immediately; an hourly cron sweep (runScheduledDeletions in scheduler.js) performs the same non-destructive soft-archive once the grace period elapses. Archived courses also now block new chat messages and discussion posts — see Communication > Course Forums remarks.
20 | User Management | CSV User Import | Done
21 | User Management | Supervisor Assignment | Done
22 | User Management | Cohort Management | Done
23 | User Management | Dormant User Management | Partial
24 | Learning Delivery | Instructor-Led Training (ILT) | Done
25 | Learning Delivery | Virtual Instructor-Led Training (VILT) | Done
26 | Learning Delivery | Waitlist Management | Done
27 | Learning Delivery | QR Code Attendance | Done
28 | Learning Delivery | Approval Workflows | Done
29 | Learning Delivery | Competency Framework | Not Started
30 | Learning Delivery | Learning Plans | Not Started
31 | AI | AI Recommendations | Partial
32 | AI | AI Quiz Generation | Done
33 | AI | Learning Analytics | Done
34 | Learning | Gamification | Partial
35 | Communication | Email Notifications | Done
36 | Communication | SMS Notifications | Not Started
37 | Communication | WhatsApp Notifications | Not Started
38 | Communication | Automated Reminders | Done
39 | Communication | Course Forums | Done | mwasalatDiscussion.service.js createThread/addReply and mwasalatChat.service.js sendMessage now return 403 once the parent course is archived ("...discussion is closed to new posts" / "...messaging is closed"). Reading existing threads/messages and instructor moderation (pin/resolve/delete) are unaffected — only new posts/messages are frozen. Ties into the new grace-period scheduled deletion in Course Management > Content Retirement.
40 | Communication | Global Announcements | Done
41 | Assessment & Certification | Quiz Engine | Done
42 | Assessment & Certification | Adaptive Assessments | Not Started
43 | Assessment & Certification | Certificate Generation | Done
44 | Assessment & Certification | Auto-renewing Certifications | Done
45 | Assessment & Certification | Survey Management | Not Started
46 | Reports & Analytics | Standard Reports | Done
47 | Reports & Analytics | Custom Reports | Partial
48 | Reports & Analytics | CPD Tracking | Not Started
49 | Reports & Analytics | Learner Transcripts | Done
50 | Reports & Analytics | Certification Reports | Done
51 | Administration | Web-based Administration | Done
52 | Administration | Configurable File Upload Limits | Partial
53 | Administration | User Timezone Support | Partial
54 | System | Background Job Scheduler | Done
55 | Security | Password Policy | Done
56 | Security | CAPTCHA Protection | Done
57 | Security | Session Timeout | Done
58 | Security | Consent Management | Done
59 | Security | Two-Factor Authentication (TOTP) | Done

## Hosting_DevOps
No. | Module | Feature | Status
1 | Infrastructure | Cloud VPS Deployment | Not Started
2 | Platform | Data Sovereignty Ready | Done
3 | Infrastructure | Redis Caching | Not Started
4 | Infrastructure | Infrastructure Scalability | Partial
5 | Security | SSL / HTTPS | Partial
6 | Security | Data Encryption at Rest | Done
7 | Infrastructure | Automated Backups | Not Started
8 | Infrastructure | System Monitoring | Done
9 | Administration | Patch Management | Done
10 | Security | SSH / Secure Server Access | Not Started

## Client_Dependencies
No. | Module | Feature | Status
1 | Branding | Custom Branding | Done
2 | Security | SAML2 SSO | Not Started
3 | User Management | LDAP / Active Directory Synchronization | Not Started
4 | User Management | Automatic User Provisioning | Not Started
5 | Security | OAuth2 Authentication | Done
6 | Integrations | HRMS Integration | Not Started
7 | Integrations | Zoom Integration | Done
8 | Integrations | Microsoft Teams Integration | Not Started
9 | Integrations | Payment Gateway Integration | Done
10 | Integrations | Google Analytics Integration | Done
11 | Communication | SMTP Configuration | Done
12 | Communication | SMS Gateway | Not Started
13 | Communication | WhatsApp Business API | Not Started
14 | AI | OpenAI/API Configuration | Done
15 | Mobile | Push Notification Configuration | Done

## Support_PostGoLive
No. | Module | Feature | Status
1 | Support | Context-sensitive Help | Not Started
2 | Support | Helpdesk Support | Not Started
3 | Support | Administrator Training | Not Started
4 | Support | Trainer Training | Not Started
5 | Support | Learner Orientation | Not Started
6 | Support | User Documentation | Not Started
7 | Support | Training Video Library | Not Started
8 | Support | Service Reporting | Not Started

## Extras & Custom Logic
Module / Theme | Extra Feature | Status
Content & Playback Controls | Forward-seek / scrub-ahead blocking on videos | Done
| Custom video player (download & Picture-in-Picture disabled) | Done
| Right-click protection on video player | Done
| Time-limited signed Cloudinary video URLs | Done
| Automatic completion at 90% watched | Done
| Multi-day PDF completion tracking | Done
| Content gating before quiz unlock | Done
Native Course Experience | Module & lesson-based course structure | Done
| Native lesson types (Video, PDF, Quiz, Assignment, Survey, etc.) | Done
| Native progress tracking | Done
Instructor Insights | Learner progress percentage | Done
| Risk-level classification | Done
| Current activity streak visibility | Done
| Days since last activity | Done
| Dedicated "Needs Attention" learner list | Done
| One-click learner encouragement messages | Done
AI Assistant | Role-based AI Assistant (Super Administrator, Platform Administrator, Department Administrator, Instructor, Learner) – AI capabilities are automatically scoped based on the user's role, providing contextual assistance, insights, and data access according to assigned permissions. | Done
Learning Engagement | Current & longest streak tracking | Done
| GitHub-style learning activity heatmap | Done
| Streak milestone notifications | Done
| Welcome-back notifications | Done
| Automated learner risk classification | Done
| Escalating inactivity reminders | Done
| Re-engagement email automation | Done
| Weekly instructor digest emails | Done
Communication & Collaboration | Course discussion forums | Done
| Private learner ↔ instructor chat | Done
| Super Admin ↔ Platform Admin private chat | Done
| Platform Admin ↔ Department Admin private chat | Done
| Instructor ↔ Platform Admin private chat | Done
| Supervisor ↔ Platform Admin private chat | Done
| IT Support ↔ Platform Admin private chat | Done
| Real-time WebSocket messaging | Done
| Live online user presence | Done
Calendar & Scheduling | Learner calendar | Done
| Instructor calendar | Done
| Today's Schedule dashboard widget | Done
Learner Experience | Favourite (starred) courses | Done